| Meeting | Fire & Rescue - Performance and Resources Board | Agenda Item |  |
| --- | --- | --- | --- |
| Meeting Date | 30th July 2018 | Report Number |  |
| Report Author: | Glenn McGuinness, Acting Chief Finance Officer |
| Presented By | Glenn McGuinness, |
| Subject | Capital Expenditure Review |
| Type of Report: | Information |

SUMMARY

Capital expenditure spend in 2017-18 was £3.9m against a budget of £11.4m. The purpose of this paper is to provide a more detailed analysis of the underspend. 
A forward projection of the capital programme and more detail on the 2018-19 budget is also provided.

RECOMMENDATIONS

The Performance and Resources Board is asked to:

- Note the Capital Expenditure position for 2017-18 and the reasons for the underspend of £7.5m.

- Note the current budget for capital expenditure in 2018-19.

- Agree a proposal to bring forward a revised capital programme 2018-19 through 2020-21 in conjunction with budget holders and the Service Leadership Team. This to include revised capital financing charges, borrowing implications and affordability.

BACKGROUND

This table below shows the capital expenditure outturn for 2017-18 and the current capital programme through 2021. A detailed analysis of the 2018-19 budget is included at appendix 1.

The variances against budget for 2017-18 are as follows:

- Service Workshops – Underspent £3.5m 2017-18, budget 2018-19 £3.0m 

This is the largest variance in 2017-18 and has the most significant potential financial impact moving forward.

The 2017-18 budget provided for the start of a £12.5m project to replace the existing service workshops. This budget was an initial estimate to be refined when the design phase and more accurate project costings were available. There is no expenditure to 
date.

The budget for 2018-19 is currently £3m the likely spend for 2018-19 cannot be determined now as the project is currently under review with our colleagues in Police as potential opportunities to share a central service workshop are considered.

Once our requirements are clearer, a revised business case will need to be prepared before any further decisions are taken on service workshops.

- Asset protection – Underspent £1.5m in 2017-18, budget 2018-19 £2.0m

The table below provides a further analysis of this variance.

The projects above will now be carried out this year; provision for this is included in the 2018-19 budget of £2.0m.

- Equipment – Underspent £583K in 2017-18, budget 2018-19 £778K

The reasons for the underspend in 2017-18 are as follows:

  - Heavy rescue pumps equipment £263K, expenditure deferred, included in 2018-19 budget.

  - 22m Hose upgrade project, £100K, still subject to agreement of specification, if this project goes ahead likely to be 2019-20.

  - UAV Drone (including Command) - £50K, deferred to 2019-20.

- Information Technology Underspent £2.0m in 2017-18, budget £2.0m 2018-19

The table below provides a further analysis of the variance in ICT spend in 2017-18

ICT capital expenditure was £2m under budget in the year; the main reasons for this are as follows:

- MDT replacement accounts for an underspend of £327K as costs at £172K were lower than the budget of £500K.

- The national Emergency Services Communication Programme (ESMCP) has been subject to delays, because of this planned capital expenditure of £1.1m has been deferred to 2018-19. The current expectation is that the system may go partially live in 2019-20.

- The Operational availability management project budget of £200K, deferred to 2018-19.

- The Integrated Automation Workflow (IAW) is no longer required, there is therefore a £500K saving against budget.

- Vehicles Overspent £99K in 2017-18, Budget 2018-19 £4.2m

The reasons for the overspend in 2017-18 are as follows:

  - Spend on new appliances were overspent by £241K this because delivery of appliance component parts were ahead of schedule. The phasing of the appliance replacement programme in 2018-19 is under review by Fleet Management, the budget for 2018-19 of £2.1m is currently likely to be significantly underspent. A request to amend the budget will be made once the review has been completed.

  - Other vehicles were £142K underspent.

RISK MANAGEMENT IMPLICATIONS

The review of capital expenditure against the profiled budget is part of the overall financial control process of the Authority. In exceptional circumstances, it allows for budget virements to ensure that under spending against budget heads can be utilised to fund expenditure against other priorities. If virements are not made, there is a risk that the Authority will miss opportunities to improve performance and meet key objectives during the year.

The review of the expenditure is one control measure to mitigate the risk of overspending the Authority’s budget for the year.

LEGAL AND EQUALITIES IMPLICATIONS

It is for the Authority to make the judgement between the constraints of affordability and the demands of the Service for capital investment. The requirements must also have regard of the requirements of the CIPFA code for Capital Financing in Local Authorities.
A review of the long-term affordability of capital expenditure will be prepared as part of the development of the medium term finance plan (2020 to 2024).

| LOCAL GOVERNMENT (ACCESS TO INFORMATION) ACT 1985 |
| --- |
| List of background documents – including appendices, hardcopy or electronic including any relevant link/s. |
| Appendix 1 Capital Budget 2018-19 |
| Proper Officer: | Acting Chief Finance Officer |
| Contact Officer: | Glenn McGuinness Acting Chief Finance Officer, Essex County Fire & Rescue Service, Kelvedon Park, London Road, Rivenhall, Witham CM8 3HB Tel: 01376 339169 glenn.mcguinness@essex.fire.gov.uk |

APPENDIX 1 – CAPITAL BUDGET 2018-19

# Text boxes

ESSEX POLICE, FIRE AND CRIME COMMISSIONER FIRE & RESCUE AUTHORITY

Essex County Fire & Rescue Service