## RAG Report
Theme | ID | Name | Description | Stage | Sponsor | Project Manager | Budget | Schedule | Scope | Benefits | Commentary | Expected completion date
Programme 2020 - (Option 2) | 814 | On-Call conversion project (including new availability bands) | Conversions of Dovercourt, South Woodham Ferrers, Waltham Abbey and Great Baddow stations from day crew to On-Call. Also conversion of Clacton second appliance from wholetime to On-Call and implementation of the new On-Call availability bandings | Delivery | Matt Furber | Lisa Hart |  |  |  |  | OCCP Stage 2 now in progress. Update to be given at November Change Board (28th November) | 2020-01-01
| 819 | Special appliance relocations | Review of the Service specialist capability asset numbers and locations following the programme 2020 options for change and agreed operational model. Delivery of any agreed movements and changes. | Delivery | Matt Furber | Vacant (Ben Pilkington) | [5 empty] | 2019-12-31
| 820 | Off-road replacement vehicles | Replacement of the existing pinzgauers as they reach end of life with asternal off-road capability vehicles. This includes specification development, procurement, training and role out. | Delivery | Dave Bill | Vacant (Ben Pilkington) | [5 empty] | 2018-12-31
| 826 | Firefighters Delivering Differently | Roll out of new approach to delivering community safety activity using experience gained in the 2015 DDiN pilot. Rolling out across all On-Call and wholetime fire stations, Firefighters will be more involved in determining what community safety activity happens in their local area and local communities engaged | Delivery | Moira Bruin | Lee Lucas | [5 empty] | 2021-03-31
Cosmos | 843 | COSMOS - Programme | Programme will deliver internally within Essex, the Emergency Services Mobile Communications Programme (ESMCP), which is a national home office programme that has been established in order to deliver the Emergency Services Network (ESN) as a replacement solution for Airwave. | Delivery | Matt Furber | Dennis Leeks |  |  |  |  | Schedule AMBER as there are still some as yet unquantified external factors that will influence our ESN Adoption roadmap; most notably this is the financial cost for the continued provision of Airwave post 12/19
|  | COSMOS - Control System Upgrades | This project is being initiated primarily to deliver the system upgrades within Control which are required for compatibility with the new ESN. This work extends across both ECFRS and Bedfordshire Fire & Rescue Service (BFRS) because of our existing Control partnership. | Initiation | Matt Furber | Paul Gardiner |  |  |  |  | See full report for update
|  | COSMOS - Sat-Nav Project |  | initiation | Matt Furber | Kerry Barker |  |  |  |  | Project on hold.
|  | COSMOS - MDTs | This project contains the operational components for the ESMCP programme, including the upgrade of Mobile Data Terminal (MDT) hardware, device replacement, coverage testing and interworking. Devices are defined as method of communicating voice and data over the ESN. | Initiation | Matt Furber | Kerry Barker |  |  |  |  | Project continues in delivery phase with the main focus of the month being on device build, testing and finalising the installation and roll out plans.
| 961 | COSMOS - Tablet computers for appliances | Project to provide Operational crews with a solution which complements the current and planned technology available to them, increases the availability of key risk and reference information, and enables the more effective delivery of further service requirements. | Initiation | Moira Bruin | Ed Thomas |  |  |  |  | See full report for update
People Structures | 806 | People Structures | The project of activity to develop an organisation that that has the resources and skills to deliver the Service strategy. This covers s rank to role, green/grey book, flexi rota review, management review II, talent pool/promotion process and core hours work streams | Delivery | Colette Black | Vacant (Ben Pilkington) |  |  |  |  | Remaining tasks identified ahead of drafting project closure report. | 2017-08-31
| 804 | Job Evaluation | Project put in place to address historical inconsistencies relating to current pay scales and the way in which they are aligned to the majority of green book roles | Delivery | Colette Black | Vacant (Ben Pilkington) | [5 empty] | 2017-03-31
People Systems | 816 | People Systems - Programme | Programme to deliver transformational change to the people systems used within the Service, including, Human Resources & Organisational Design Business Solution, Operational Availability Management and e-learning. | Delivery | Matt Furber | Peter Morath |  |  |  |  | The programme is in progress.
| 816 | People Systems - HR&OD Business System | To procure and implement and replacement Human Resources & Organisational Design Business Solution for our existing SAP system | Delivery | Matt Furber | Dena Morrison |  |  |  |  | The project is in progress. | 2018-04-30
| 815 | People Systems - Operational availability Management | This project is gather requirements for an improved system to manage operational availability following the implementation of the HOBS project. | Initiation | Matt Furber | Hollie Nicholson-Thomas |  |  |  |  | The Operational Availability Management (OAM) project is on hold. This is due to the priorities of the Service being altered. The OAM project will restart in late 2018.
Other | 953 | IRS Upgrade | Upgrade of IRS to version 3.1.1, migration to a new back end SQL infrastructure and the implementation of a new interface with Remsdaq 4i. | Delivery | Tracy King | Vacant (Ben Pilkington) |  |  |  |  | Go live on hold pending Remsdaq upgrade as key functionality not available in current version
| 958 | Service Wide Multi-Media Displays | Deployment of a standard build for multi-media equipment across all sites and delivery ok ‘kiosk’ mode logon to simplify access to service messages and resources | Initiation | Matt Furber | Ed Thomas |  |  |  |  | see full report for update
|  | Mobile telephone replacement | Replacement of mobile telephones. | Intiation | Matt Furber | Hannah Wakeman |  |  |  |  | work currently on hold, whilst the project is re-scoped
`