## 1 Comp Management
Reporting Period : To 1 February 2019 | Project Title | Competency Management System (TASK) |  |  |  |  | Overall Project Status | Green
Project Objective | Deliver a working competency management system. | [5 empty] | Accountable lead(s) | Colette Black
Status Update |  | Key Milestone |  |  |  | Progress % | Status | Due Date
Tactical: Following initial analysis of the TASK data, it has become apparent that there are gaps within both the data, resulting in missing TASK books, and the reports available from TASK. The data is significantly out of date and has become difficult to maintain. To address these issues, the following activities are planned: 1. Review reporting requirements and develop new reports. 2. Introduce a workflow process to notify the TASK administrators when there are operational staff changes. 3. Rebuild the TASK user tables with current HR data from Civica. 4. Investigate options to provide a 'collective approval' method of task activities for line managers. Strategic: Project Identification Document (PID) in development. Engagement with Civica to review gaps in functionality. Initial findings are that further development work is required by Civica. Meeting arranged with Purchasing & Supply to plan a PIN for suppliers to then express an interest and arrange for demos. Engagement with Operational staff to help shape the detailed requirements. |  | Tactical activities |  |  |  | 10% | On-track | 2019-05-01
|  | Assessment of high level requirements again Civica functionality |  |  |  | 100% | Complete | 2019-01-24
|  | Project Identification Document |  |  |  | 10% | On-track | 2019-03-22
|  | Supplier demonstrations (dependant on availability and response to PIN) |  |  |  | 0% | On-track | 2019-04-01
Activities Achieved this period |  |  |  | Activities Planned next period
• Initial analysis and planning of tactical solution. • Demonstration of the system by Steve King. • Scheduling of meetings with Operational users. |  |  |  | • Development of the Project Identification Document • Development of reports • Test the provision of external access to TASK (ICT)
Key Activity Risks and Issues | [6 empty] | Overall Risk Status | Green
Risks and issues are defined within the Project Identification Document
Benefits | [6 empty] | Overall Benefits Identification | Green
Projected - Cashable Benefits |  |  |  | Projected - Non Cashable
Delivery Period: | Projected - Cashable Benefits will be defined Project Identification Document |  |  | Projected - Non Cashable Benefits will be defined Project Identification Document
£ '000s
RAG definitions | Overall Project Status |  | Overall Benefits Identification |  | Overall Risk Status |  |  | Milestone Status
Red | Critical Issues that significantly threaten delivery, cost or benefits and need to be escalated to SGB and senior forums in each agency (ECFRS SLT, EP COG and EEAS SLB) for resolution. |  | Benefits still to be identified and quantified against the Home Office model; or benefits realised are less than 50% of projected |  | No Risk register in place and/or project is outside of agreed timescales/plan of delivery and/or approved budget with no plans for mitigation. |  |  | Action Required
Amber | Critical issues that significantly threaten delivery, cost or benefits but are capable of being managed at programme board level |  | Benefits identified but assumptions and methods for quantifying to be developed; or benefits being realised but unlikely to be realised within 25% sensitivity analysis. |  | Risk Register in place but project outside of agreed timescales, plan and/or approved budget but mitigation plans are in place |  |  | On-track
Green | The project is on track and can be managed through normal project/programme delivery process. |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  |  | Concern
Complete

## 2 OAM
Reporting Period : To 1 February 2019 | Project Title | Operational Availability Management (ERB) |  |  |  |  | Overall Project Status | Green
Project Objective | Replace the existing ClickSoftware Electronic Rota Book (ERB) with an internally developed solution. This will include development of a core availability management system, the automation of the ASW process to identify gaps and propose resources, and to integrate the solution with Remsdaq 4i to maintain the status of appliances based on crewing availability levels. | [5 empty] | Accountable lead(s) | Matt Furber
Status Update |  | Key Milestone |  |  |  | Progress % | Status | Due Date
The Project Brief is complete and absorbs the ASW Automation Project and planned integration with Remsdaq 4i. The Project Brief is with stakeholders for review ahead of formal submission to the Change Board for approval. The following are the anticipated outcomes of the project: • Introduction of a system to manage availability across all duty types • Integration with Civica HR & Payroll • Integration with the Electronic Tally Board, Global Availability Board and SMS Module • Introduction of a process to automate the resource selection process for ASWs • Integration with the Control mobilising system, Remsdaq 4i, to manage appliance availability and crewing information • Development of an electronic riders board to capture accurate crewing information • Migrate appropriate data from the existing Clicksoftware ERB solution • Ensure compliance with the Working Time Directive (WTD) • Ensure compliance with the Dispute Resolution requirements • Ensure complaince with the Operational Grey Book requirements • Appropriate reporting, available to all levels • The development of the appropriate processes to support any new ways of working • The provision of all necessary training and support materials as required • The ERB application, associated support, ICT infrastructure and licensing is removed and the platform decommissioned |  | Delivery of the Project Brief |  |  |  | 90% | On-track | 2019-02-15
|  | Delivery of the Project Identification Document (PID) |  |  |  | 0% | On-track | 2019-03-15
|  | Project Design Phase |  |  |  | 0% | On-track | 2019-04-01
Activities Achieved this period |  |  |  | Activities Planned next period
• Completion of the Project Brief |  |  |  | • Approval of the Project Brief • Development of the Project Identification Document • Risk and issue workshop • Prototype the core availability module and identification of up and downstream impacted systems • Rep body engagement • Communications planning activities
Key Activity Risks and Issues | [6 empty] | Overall Risk Status | Green
A workshop with Operations and Control stakeholders is planned to identify and classify the risks associated with this work.
Benefits | [6 empty] | Overall Benefits Identification | Green
Projected - Cashable Benefits |  |  |  | Projected - Non Cashable
Delivery Period: | The forecast delivery period for the core functionality is Q4 2019 |  |  | The following non-cashable benefits are anticipated: • Reduction in support effort required by ICT Service Delivery • Real-time crewing levels will drive appliance availability, reducing the need for Station to Control phone calls • Reduction in effort to process Additional Shift Working, enabling multiple ASW requests to be managed in parallel • De-duplication of data, with Civica HR & Payroll being the single version of the truth for resourcing information • Business logic enabling stricter compliance with the Working Time Directive and the Dispute Resolution • Station-based electronic rider board, ensuring real-time resource management information is available • Improved accuracy of availability data • Development of processes and procedures to industrialise and support internal development within the Service
£ '000s | The following cashable benefits are anticipated: • £66,000 - reduction in Clicksoftware license and support costs • c£10,000 - reduction in ICT infrastructure (servers, backups, networking) • c£20,000 - cost savings attributed to the resource hours saved through efficiency gains (estimated)
RAG definitions | Overall Project Status |  | Overall Benefits Identification |  | Overall Risk Status |  |  | Milestone Status
Red | Critical Issues that significantly threaten delivery, cost or benefits and need to be escalated to SGB and senior forums in each agency (ECFRS SLT, EP COG and EEAS SLB) for resolution. |  | Benefits still to be identified and quantified against the Home Office model; or benefits realised are less than 50% of projected |  | No Risk register in place and/or project is outside of agreed timescales/plan of delivery and/or approved budget with no plans for mitigation. |  |  | Action Required
Amber | Critical issues that significantly threaten delivery, cost or benefits but are capable of being managed at programme board level |  | Benefits identified but assumptions and methods for quantifying to be developed; or benefits being realised but unlikely to be realised within 25% sensitivity analysis. |  | Risk Register in place but project outside of agreed timescales, plan and/or approved budget but mitigation plans are in place |  |  | On-track
Green | The project is on track and can be managed through normal project/programme delivery process. |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  |  | Concern
Complete

## 3 CRM
2019-02-13 | Project Title | CRM |  |  |  |  | Overall Project Status | Red
Project Objective | To resolve issues with workflow, data, ways of working and use of the CRM system in the CFS, TFS, Water, Performance and Operations departments. | [5 empty] | Accountable lead(s) | Moira Bruin
Status Update |  | Key Milestone |  |  |  | Progress % | Status | Due Date
The Service implemented a Microsoft Dynamics CRM (Customer Relations Management) solution to replace the legacy Management Information System, going live in 2016. The CRM is intended to be the primary information system for CFS, TFS and Water section. Despite the implementation and closure of the DELTA programme, issues have been raised in a number of business areas and projects which suggest that further work on the CRM system and/or the use of CRM is required. Three workshops have been held with a range of users, technical experts and support from Hitachi (the supplier). These have worked through a process to identify, agree and prioritise the issues. Work streams were set up to investigate and, where possible, rectify the highest priority work streams. It is clear despite significant enthusiasm and effort from work-stream stakeholders, the issues are unlikely to be resolved without additional, specific technical resources. Most important of these is to recruit a suitably experienced system owner who can lead on the rectification of the issues, acting as a central point of contact for users, ICT, Hitachi and other suppliers and a pan-organisational, systems approach (for example looking at the interdependencies and appropriate sequencing of work). There is little specialist CRM knowledge in the ICT team so in addition to the CRM System Owner it likely that additional technical resources will be required. These additional resources are likely to be required for the next 12-18 months. |  | Key stakeholders attend series of workshops to identify and prioritise key work-streams and activities on CRM according to organisational risk. |  |  |  | 100% | Complete | 2019-01-17
|  | Work stream leads identified and remedial activities identified. Resourcing requirements identified. |  |  |  | 60% | Action Required | 2019-01-17
|  | Recruit CRM system owner to identify ways to resolve known issues and deliver improvements both in terms of system working (in conjunction with CRM development resource) and ways of working/interactions. This post will also be SPOC with Hitachi |  |  |  | 0%
Review of initial business case and design documentation to clarify to what extent the solution fits current needs.
Recruit CRM developer/specialist in conjunction with CRM system owner to undertake technical changes and improvements on an ongoing basis.
Activities Achieved this period |  |  |  | Activities Planned next period
• Work-shop held on 17th January with key stakeholders to review progress on work streams • Identified resource requirement for remediation activity • Resolved system issue preventing TFS activity |  |  |  | • Establish a project board • Create role profiles and job descriptions for specialist posts. • Progress recruitment for specialist reports
Key Activity Risks and Issues | [6 empty] | Overall Risk Status | Red
• This work is a control measure against SRR10015 - False or inaccurate data limits the Service's future planning and decision making leading to the Service being unable to plan or deliver an effective or efficient service. • Key issues this period o There is a backlog of data to be input into CRM in CFS from 2016/17 o TFS ceased audit activity and redeployed staff to other activities between December 2018 and January 2019 as CRM issues meant that data could not be recorded o The organisation cannot extract performance data regarding TFS from CRM and this is likely to impact on our data returns to HMICFRS and the Home Office. o Risk information updates are having to made manually as there is no automatic process through CRM.
Benefits | [6 empty] | Overall Benefits Identification | Red
Projected - Cashable Benefits |  |  |  | Projected - Non Cashable
Delivery Period: |  |  |  | Current feedback suggests the identified, non-cashable benefits of the initial project have not been realised fully. Resolving the issues experienced by the user base will facilitate future benefits realisation.
£ '000s | The review of the business case (identified in the 4th key milestone above) will consider this initial cashable benefits and whether these are likely to be realised.
RAG definitions | Overall Project Status |  | Overall Benefits Identification |  | Overall Risk Status |  |  | Milestone Status
Red | Critical Issues that significantly threaten delivery, cost or benefits and need to be escalated to SGB and senior forums in each agency (ECFRS SLT, EP COG and EEAS SLB) for resolution. |  | Benefits still to be identified and quantified against the Home Office model; or benefits realised are less than 50% of projected |  | No Risk register in place and/or project is outside of agreed timescales/plan of delivery and/or approved budget with no plans for mitigation. |  |  | Action Required
Amber | Critical issues that significantly threaten delivery, cost or benefits but are capable of being managed at programme board level |  | Benefits identified but assumptions and methods for quantifying to be developed; or benefits being realised but unlikely to be realised within 25% sensitivity analysis. |  | Risk Register in place but project outside of agreed timescales, plan and/or approved budget but mitigation plans are in place |  |  | On-track
Green | The project is on track and can be managed through normal project/programme delivery process. |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  |  | Concern
Complete

## 4 4i, IRS, ICCS
4
| Reporting Period : To 12 February 2019 | Project Title | Resque 4i, IRS and 3020 ICCS Upgrades |  |  |  |  | Overall Project Status | Green
| Project Objective | Upgrade the current ECFRS Control Systems, in order to maintain Support & Maintenance contracts with Remsdaq and Frequentis until January 2021. Upgrade IRS in parallel with Resque 4i, in order to resolve current interface issues and meet ECFRS statutory reporting requirements. | [5 empty] | Accountable lead(s) | Matt Furber
| Status Update |  | Key Milestone |  |  |  | Progress % | Status | Due Date
| Remsdaq have now completed the build and data migration for the new Resque 4i Development environment. ECFRS have commenced initial data and system verification testing, but have identified a few issues that have been referred back to Remsdaq. Currently reviewing previous documentation and plan for IRS upgrade, in order to establish what's required to complete testing and transition in parallel with the Resque 4i upgrade. The OPFCC has now approved the 3020 ICCS upgrade to version 2.9 with a hardware refresh, in order to provide ECFRS and BFRS with a supportable ICCS until 2022 (if required). Frequentis have been informed of our decision and will now provide us with a formal Offer by the end of February. |  | Delivery of new Resque 4i Development environment |  |  |  | 100% | Complete | 2019-01-31
|  |  | Delivery of new IRS Development environment |  |  |  | 90% | On-track | 2019-02-28
|  |  | Formal Offer from Frequentis |  |  |  | 50% | On-track | 2019-02-28
|  |  | Updated PFCC Decision Sheet for 3020 ICCS Upgrade and Support & Maintenance |  |  |  | 0% | On-track | 2019-03-15
| Activities Achieved this period |  |  |  | Activities Planned next period
| • Delivery of new Resque 4i Development environment • Commencement of ECFRS initial data and system verification testing • Identification of previous IRS upgrade documentation and plan • Formal proposal received from Frequentis regarding the options for extension of Operational Services beyond the current contract expiry date • Informed Frequentis of our decision to upgrade 3020 ICCS to version 2.9 |  |  |  | • Remsdaq to resolve initial issues with new Resque 4i Development environment • Engage ICT and Performance & Data regarding current status of IRS upgrade and Development environment • Draw up project and test plans for Resque 4i and IRS upgrades • Formal letters to Remsdaq and Frequentis confirming our plans and extension of current Support & Maintenance contracts to January 2021 • Formal Offer from Frequentis for 3020 ICCS upgrade to version 2.9 and hardware refresh • Revised proposal from Remsdaq for extension of Support & Maintenance • Updated PFCC Decision Sheet to request funding for ICCS upgrade, as a dependency for extension of current ECFRS Control Systems contracts to 13 January 2021
| Key Activity Risks and Issues | [6 empty] | Overall Risk Status | Green
Key Activity Risks and Issues identified to date: - • SDCON0006: Frequentis 3020 ICCS upgrade and/or hardware refresh maybe cost prohibitive. Frequentis have provided total indicative costs of approximately £100k, but this won't be confirmed until we receive the formal Offer
| Benefits | [6 empty] | Overall Benefits Identification | Green
| Projected - Cashable Benefits |  |  |  | Projected - Non Cashable Benefits
| Delivery Period: | All Benefits will be delivered as soon as the project is delivered. Initial delivery period for continued Support & Maintenance will be to January 2021, but could be extended to the end of 2022, if required. |  |  | Projected - Non Cashable Benefits: - • Mitigation of Operational Risk of unsupported Resque 4i system, initially to January 2021 • Mitigation of Operational Risk of unsupported Frequentis ICCS system, initially to January 2021 • Compliance with ECFRS statutory Incident reporting requirements • Increased timescales to procure and transition to new Control Systems
| £ '000s | Not yet identified, as primary benefits of the project are Non Cashable.
| RAG definitions | Overall Project Status |  | Overall Benefits Identification |  | Overall Risk Status |  |  | Milestone Status
| Red | Critical Issues that significantly threaten delivery, cost or benefits and need to be escalated to SGB and senior forums in each agency (ECFRS SLT, EP COG and EEAS SLB) for resolution. |  | Benefits still to be identified and quantified against the Home Office model; or benefits realised are less than 50% of projected |  | No Risk register in place and/or project is outside of agreed timescales/plan of delivery and/or approved budget with no plans for mitigation. |  |  | Action Required
| Amber | Critical issues that significantly threaten delivery, cost or benefits but are capable of being managed at programme board level |  | Benefits identified but assumptions and methods for quantifying to be developed; or benefits being realised but unlikely to be realised within 25% sensitivity analysis. |  | Risk Register in place but project outside of agreed timescales, plan and/or approved budget but mitigation plans are in place |  |  | On-track
| Green | The project is on track and can be managed through normal project/programme delivery process. |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  |  | Concern
Complete

## 5 Digital Strategy
Reporting Period : To 13 February 2019 | Project Title | Digital Strategy |  |  |  |  | Overall Project Status | Green
Project Objective | Develop a draft digital strategy for the Service. | [5 empty] | Accountable lead(s) | Ben Pilkington
Status Update |  | Key Milestone |  |  |  | Progress % | Status | Due Date
Primarily a research and engagement phase at present. Considering the art of what is possible with internal stakeholders and external best practice and examples. The need to move forward with our infrastructure and particularly the desktop is now high lighted in a number of areas (intranet, CRM, business intelligence). Moving forward needs to be done in a coordinated manner. |  | Digital strategy update paper to SLT |  |  |  | 50% | On-track | 2019-02-26
|  | Assesmnet of current ICT infrastructure |  |  |  | 10% | On-track | 2019-03-31
|  | Draft digital strategy to SLT |  |  |  | 20% | On-track | 2019-04-23
Activities Achieved this period |  |  |  | Activities Planned next period
Continued research with other organisations’ digital strategies Engagement with internal stakeholders to identify aspirations Researched AgilePM as a delivery method for digital change |  |  |  | Draft update paper for SLT Continue internal engagement to understand the requirmeents of users and fucntions Undertake an assessment of the current skills and confidence with technology across the service. Begin piloting agile delivery methods- CRM and intranet Assesment of current ICT infrasturcture begins Investigation of licensing options
Key Activity Risks and Issues | [6 empty] | Overall Risk Status | Red
Linked to existing Strategic risk (SRR150026 - Failure in the Service's Information, Communication and Technology (ICT) infrastructure, leading to intermittent or loss of service or current ways of working are not fit for purpose). Progressing away from some of the end of life equipment will need a coordinated approach to the decisons to be made.
Benefits | [6 empty] | Overall Benefits Identification | Red
Projected - Cashable Benefits |  |  |  | Projected - Non Cashable
Delivery Period: |  |  |  | None identified at this point. Benefits are likely to include; increased user satisafation and engagement better outcomes for the public
£ '000s | None identified at this point in the process. Benefits will be called out in the strategy.
RAG definitions | Overall Project Status |  | Overall Benefits Identification |  | Overall Risk Status |  |  | Milestone Status
Red | Critical Issues that significantly threaten delivery, cost or benefits and need to be escalated to SGB and senior forums in each agency (ECFRS SLT, EP COG and EEAS SLB) for resolution. |  | Benefits still to be identified and quantified against the Home Office model; or benefits realised are less than 50% of projected |  | No Risk register in place and/or project is outside of agreed timescales/plan of delivery and/or approved budget with no plans for mitigation. |  |  | Action Required
Amber | Critical issues that significantly threaten delivery, cost or benefits but are capable of being managed at programme board level |  | Benefits identified but assumptions and methods for quantifying to be developed; or benefits being realised but unlikely to be realised within 25% sensitivity analysis. |  | Risk Register in place but project outside of agreed timescales, plan and/or approved budget but mitigation plans are in place |  |  | On-track
Green | The project is on track and can be managed through normal project/programme delivery process. |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  |  | Concern
Complete

## 6 Intranet development
Reporting Period : To 1 February 2019 | Project Title | Intranet development - phase one |  |  |  |  | Overall Project Status | Amber
Project Objective | Update the current intranet site to: 1. Become a trusted source that staff use as the first place to find information 2. Improve accessibility and search functionality making it quicker and easier for colleagues to find information they need to do their jobs, regardless of their work location | [5 empty] | Accountable lead(s) | Emily Cheyne
Status Update |  | Key Milestone |  |  |  | Progress % | Status | Due Date
After meetings with ICT and Ben Pilkington, it has been agreed that currently the only viable option is to use the existing platform (Pingala), but review the content and design. This will be PHASE ONE development. PHASE TWO (new intranet and platform that will create a enhanced digital experience and two way engagement channel) will form part of the digital strategy. |  | Current intranet- audit of content. EC to review to complete |  |  |  | 90% | On-track | 2019-02-19
|  | Current inranet - review of editors and content up to date |  |  |  | 75% | On-track | 2019-02-25
|  | Terms of reference (Agile) |  |  |  | 5% | On-track | 2019-02-28
|  | Stakeholders identified |  |  |  | 100% | Complete
Redesign of homepage
Engagement and involvement - employees
Site map approved
Intranet build - with pingala
New content
Launch plan - comms and engagement
User training - identified users
Activities Achieved this period |  |  |  | Activities Planned next period
• content and layers audited • intranet editors contacted and updated pages • decision re platform to use |  |  |  | • Complete terms of reference • Approved design • Approved site map
Key Activity Risks and Issues | [6 empty] | Overall Risk Status | Green
Benefits | [6 empty] | Overall Benefits Identification | Red
Projected - Cashable Benefits |  |  |  | Projected - Non Cashable
Delivery Period:
£ '000s
RAG definitions | Overall Project Status |  | Overall Benefits Identification |  | Overall Risk Status |  |  | Milestone Status
Red | Critical Issues that significantly threaten delivery, cost or benefits and need to be escalated to SGB and senior forums in each agency (ECFRS SLT, EP COG and EEAS SLB) for resolution. |  | Benefits still to be identified and quantified against the Home Office model; or benefits realised are less than 50% of projected |  | No Risk register in place and/or project is outside of agreed timescales/plan of delivery and/or approved budget with no plans for mitigation. |  |  | Action Required
Amber | Critical issues that significantly threaten delivery, cost or benefits but are capable of being managed at programme board level |  | Benefits identified but assumptions and methods for quantifying to be developed; or benefits being realised but unlikely to be realised within 25% sensitivity analysis. |  | Risk Register in place but project outside of agreed timescales, plan and/or approved budget but mitigation plans are in place |  |  | On-track
Green | The project is on track and can be managed through normal project/programme delivery process. |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  | Benefits mapped and will be achieved within 25% sensitivity analysis |  |  | Concern
Complete