## RAG Report
Theme | ID | Name | Description | Stage | Sponsor | Project Manager | Budget | Schedule | Scope | Benefits | Commentary | Expected completion date | Revenue Budget | Capital Budget | Project completion date
Programme 2020 - (Option 2) | 819 | Special Appliance Relocations | Review of the Service specialist capability asset numbers and locations following the programme 2020 options for change and agreed operational model. Delivery of any agreed movements and changes. | Delivery | Matt Furber | Ben Pilkington | [5 empty] | 2019-12-31 | 521831 |  | 2019-11-01
| 820 | Off-Road Vehicle Replacement | Replacement of the existing pinzgauers as they reach end of life with asternal off-road capability vehicles. This includes specification development, procurement, training and role out. | Delivery | Matt Furber | Vacant (Ben Pilkington) |  |  |  |  | Vehicle expected to with ECFRS in May, training plan being revised with updated timeframe. Aspiration to have one vehcile on the run ahead of the summer | 2018-12-31 | 35000 | 655896 | 2018-12-01
| 826 | Firefighters Delivering Differently | Roll out of new approach to delivering community safety activity using experience gained in the 2015 DDiN pilot. Rolling out across all On-Call and wholetime fire stations, Firefighters will be more involved in determining what community safety activity happens in their local area and local communities engaged | Closure | Moira Bruin | Lee Lucas |  |  |  |  | Closure report on the agenda for February. | 2021-03-31 | 637000 |  | 2021-03-01
On-call Development Programme |  | On-Call Development - Programme | A rewarding, flexible and effective duty system, that meets the needs of our people, the Service and the communities we serve. | Definition | Jo Turton | Lisa Hart
|  | On-Call conversion project (including new availability bands) | Conversions of Dovercourt, South Woodham Ferrers, Waltham Abbey and Great Baddow stations from day crew to On-Call. Also conversion of Clacton second appliance from wholetime to On-Call and implementation of the new On-Call availability bandings | Delivery | Dave Bill | Lisa Hart |  |  |  |  | On-Call Conversion Project in progress - phase 2. Issues relating to assessment day and recruit training scheduling/availability referred to Project Board. Scheudle - Proposed extension / phased approach, Pay protection / settlement agreement, ‘Registration of interest’ letter to DC employees and FAQ documents delayed pending response from RB |  | 1574902 |  | 2021-03-01
|  | Day Duty Officers Riding Project |  | Pilot | Dave Bill | Jim Palmer |  |  |  |  | More information to be reported next period
|  | On-Call Contracts Project |  | Initiation | Colette Black | Steve Tovey |  |  |  |  | More information to be reported next period
|  | On-call Availability Project |  | Initiation | Dave Bill | Steve Tovey |  |  |  |  | More information to be reported next period
Cosmos | 843 | COSMOS - Programme | Programme will deliver internally within Essex, the Emergency Services Mobile Communications Programme (ESMCP), which is a national home office programme that has been established in order to deliver the Emergency Services Network (ESN) as a replacement solution for Airwave. | Delivery | Matt Furber | Matthew Stalker |  |  |  |  | Programme is in the delivery phase; Schedule AMBER as although the local Programme activity is progressing well, there remains significant uncertainty as to when the National ESMCP will make the ESN available for Services to transition to and adopt. |  |  | 300000 | 2023-03-01
|  | COSMOS - Control System Upgrades | This project is being initiated primarily to deliver the system upgrades within Control which are required for compatibility with the new ESN. This work extends across both ECFRS and Bedfordshire Fire & Rescue Service (BFRS) because of our existing Control partnership. | Initiation | Matt Furber | Paul Gardiner |  |  |  |  | An initial Project Initiation Document has now been completed to a 70% confidence level, but was not approved, due to the significant costs and increase in timescales since the Project Brief was approved in June 2018. |  |  | 600000 | (PID) Sep -18
|  | COSMOS - Sat-Nav Project |  | Initiation | Matt Furber | Kerry Barker |  |  |  |  | On hold |  |  | 100000
|  | COSMOS - MDTs | This project contains the operational components for the ESMCP programme, including the upgrade of Mobile Data Terminal (MDT) hardware, device replacement, coverage testing and interworking. Devices are defined as method of communicating voice and data over the ESN. | Delivery | Matt Furber | Kerry Barker |  |  |  |  | Project completes phase 1 (front line appliance) delivery on 13 February. Focus has been on reviewing feedback and finalising phase 2 (specialist appliances) plans, scheduled for March. |  | 220000 | 250000 | 2019-03-01
| 961 | COSMOS - Tablet computers for appliances | Project to provide Operational crews with a solution which complements the current and planned technology available to them, increases the availability of key risk and reference information, and enables the more effective delivery of further service requirements. | Delivery | Moira Bruin | Ed Thomas | [6 empty] | 90000 | 190000 | 2019-03-01
People Structures | 806 | People Structures | The project of activity to develop an organisation that that has the resources and skills to deliver the Service strategy. This covers s rank to role, green/grey book, flexi rota review, management review II, talent pool/promotion process and core hours work streams | Closure | Colette Black | Vacant (Ben Pilkington) |  |  |  |  | Closure | 2017-08-31 |  |  | 2018-12-01
| 804 | Job Evaluation | Project put in place to address historical inconsistencies relating to current pay scales and the way in which they are aligned to the majority of green book roles | Closure | Colette Black | Vacant (Ben Pilkington) |  |  |  |  | Closure | 2017-03-31
People Systems | 816 | People Systems - Programme | Programme to deliver transformational change to the people systems used within the Service, including, Human Resources & Organisational Design Business Solution, Operational Availability Management and e-learning. | Delivery | Matt Furber | Peter Morath
| 816 | People Systems - HR&OD Business System | To procure and implement and replacement Human Resources & Organisational Design Business Solution for our existing SAP system | Delivery | Matt Furber | Dena Morrison | [5 empty] | 2018-04-30 | 320000 | 280000 | 2018-12-01
|  | ASW Automation | Automation of processes for managing Additonal Shift Working | Intiation | Matt Furber | Peter Morath |  |  |  |  | Will now incorporate into OAM project
| 815 | People Systems - Operational availability Management | This project is gather requirements for an improved system to manage operational availability following the implementation of the HOBS project. | Initiation | Matt Furber | Peter Morath |  |  |  |  | The Operational Availability Management (OAM) project is on hold. This is due to the priorities of the Service being altered. The OAM project will restart in late 2018. |  |  | 250000
Other | 953 | IRS Upgrade | Upgrade of IRS to version 3.1.1, migration to a new back end SQL infrastructure and the implementation of a new interface with Remsdaq 4i. | Delivery | Matt furber | Paul Gardner |  |  |  |  | Now incorporated into work with 4i and ICCS upgrade. |  | 20000 |  | 2019-03-01
| 958 | Service Wide Multi-Media Displays | Deployment of a standard build for multi-media equipment across all sites and delivery ok ‘kiosk’ mode logon to simplify access to service messages and resources | Delivery | Matt Furber | Ed Thomas | [6 empty] | 65000 | 250000 | 2019-07-01
|  | Mobile telephone replacement | Replacement of mobile telephones. | Delivery | Matt Furber | Hannah Wakeman |  |  |  |  | Project is active Build work complete. Awaiting decision on rolling out with our internal phone build or a collaborative, Essex Police build. |  |  | 50000 | 2019-03-01
`

## Completed projects
ID | Name | Description | Stage | Sponsor | Project Manager | Budget | Schedule | Scope | Benefits | Commentary
| HR Service desk phase 2 | Replacement of spreadsheets for case files in to HR Cherwell | Complete | Collette Black | Hannah Phipps |  |  |  |  | Already complete before reporting process commenced.
| Firewall Review | Upgrade of all firewalls to latest version and a review of the rule base to remove unnecessary rules. | Complete | Jan Swanwick | Dennis Leeks |  |  |  |  | Already complete before reporting process commenced.
| Control | Procurement and implementation of a new control mobilising system | Complete | Dave Bill | Paul Gardiner
818 | Removal of Frinton Second appliance | Removal of Frinton's second appliance from operational service. | Delivery | Dave Bill | Mark Wilby |  |  |  |  | (Not set up as a project) Appliance will be removed from operational service on 3/01/2018 in line with the original plan.
824 | Home Fire Safety model | The purpose of this project is to develop a structured concept of Level 1 and Level 2 Safe and Well visits for ECFRS and roll out their delivery. | Delivery | Moira Bruin | Andrea MacAlister |  |  |  |  | Project Closed. Closure Report of April Chang eboard Agenda. | 2018-01-31
| XP & Windows 2003 Remediation | Removal of out of support operating systems, Windows XP and Windows Server 2003, from the ECFRS estate. | Delivery | Jan Swanwick | Martin Chester |  |  |  |  | Project Closed. Closure report requested.
954 | Workshops telephony system replacement | Replacing legacy telephony system at Workshops with a Skype based solution | Delivery | Jan Swanwick | Ed Thomas |  |  |  |  | Remove from JCAD when project closed. | Y

## RAG definitions
| Budget | Schedule | Scope | Benefits | Implications
Red | Committed spend is forecast to be outside the upper budget tolerance. | Planned activity continues beyond the schedule tolerance. | A change in the scope fo the project is required. | The benefits are not going to be realised. | A red score implies that the project/programme is likely to be out of its agreed tolerances. The board will need to take corrective measures. Projects should submit an exception report with a recommended course of action - including any requried change to tolerance.
Amber | There is a risk that that the spend will be outside the upper budget tolerance. | There is a risk that the project may not complete within the schedule tolerance. | There is a risk that the project scope may need to change | There is a risk that the beneftis will not be realised | An amber score indicates that action is required but which may be taken within the project /programme rather than requiring a change board decision.
Green | Spend is forecast to be withinn the budget tolerance. | The project is predicted to complete within the schedule tolerance. | The scope is not changed. | The benefits are still expected to be realised. | A green score means that no action is required.
Grey |  |  |  |  | Reserved for projects which have actively been placed on hold by the Change Board.