## Investments Timetable
Investment - Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Last Yr's Meeting Date | Date of Meeting | Comments
IO1 | Investment - Other | Senior Leadership Team | Strategic Change | Claire Heath | 2021-03-23 | 2023-06-20 | Strategic and Service Demand Pressures from FMS (some may not fall within remit of Officer Growth)
IO2 | Investment - Other | Revenue Budget Bid Templates Issued | Corporate Finance | Chief Accountant | 2021-06-25 | 2023-06-26 | Template issued to Finance Business Partners and Management Accountants. FBPs and MAs will liaise with Budget Holders to capture bids.
IO3 | Investment - Other | Start engagement with Budget Holders to capture contractural & legal and service demand investment | Business Partnering and Management Accounting | BPs and MA s | 2021-07-23 | 2023-06-26 | Finance Business Partners (FBPs) and Management Accountants (MAs)will work with budget holders where there are confirmed contractural, legal or service demand pressures. BPs and MAs responsible for submitting bid documentation that has been completed with input from subject matter experts within commands.
IO4 | Investment - Other | Deadline for submission of contractural, legal and service priority business cases. | Force Commands | BPs and MA s | 2021-08-31 | 2023-09-01 | This will allow time for QA of bids prior to being forwarded for 7 Pillar Assessment
IO5 | Investment - Other | QA and review of detailed growth investment completed | Business Partnering and Management Accounting | BPs and MA s | 2021-09-06 | 2023-09-11 | Finance Business Partners and Management Accountants provide detailed bids that have been signed off by Chief Officers to Chief Accountant for consolidation. (Includes FMS identified strategic bids). At this point they are submitted to Strategic Change for 7 Pillar assessment.
IO6 | Investment - Other | 7 Pillar Assessment of Bids | Strategic Change | Anna Hook | 2021-09-27 | 2023-10-05 | 7 Pillar Assessment completed and returned to Corporate Finance for submission to Extraordinary Budget Setting SCCB
IO7 | Investment - Other | SCCB (Extraordiary Budget Setting) | Corporate Finance | CFO / Chief Accountant | 2021-10-08 | Thur-12-Oct | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment.
From this point follow 'Strategic' timetable

## Savings Timetable
Savings - Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Last Yr's Meeting Date | Date of Meeting | Comments | Completed
S1 | Savings | Efficiency Savings and Growth Board |  |  |  | 2023-03-07 | Share Budget Setting Timetable.
S2 | Savings | COG | Corporate Finance / Strategic Change | Anna Hook / Debbie Martin |  | TBC | Paper to consider approach to identifying transformation savings
S2 | Savings | SLT - Savings and Efficiencies Challenge | Corporate Finance | Debbie Martin | 2021-04-22 | 2023-06-20 | Briefing to SLT on the savings challenge | yes
S3 | Savings | Templates to capture Savings distributed (High level and Detailed) | Corporate Finance | Annette Chan / Anna Hook | 2021-04-28 | 2023-06-23 | Deadline for submission will be 21st August (liaise with Strategic Change and Finance Business Partners if Business Case is required) | yes
S4 | Savings | Efficiency Savings and Growth Board | Strategic Change | Anna Hook | 2021-06-07 | 2023-07-11 |  | yes
S5 | Savings | Submission deadline for savings templates | Force Commands | Chief Officers/Anna Hook |  | 2023-08-21 | Submit to Finance Business Partner (Strategic Change)
S6 | Savings | Commence QA of Savings Proposals | Strategic Change/Corporate Finance | Finance BP (Strategic Change)/Debbie Martin | 2021-07-13 | 2023-08-22 | Quality Assurance of Savings Proposals
S7 | Savings | Corporate Finance Non Pay Star Chamber: 1 of 3. | Corporate Finance | BPs and MA s | 2021-09-01 | 2023-08-29 | Review of current year forecasts to identify potential saving areas (ensuring no overlap with other savings proposals)
S8 | Savings | Efficiency Savings and Growth Board | Strategic Change / Corporate Finance | Debbie Martin / Anna Hook | 2021-10-11 | 2023-09-12 | Overall Consolidated Growth Programme (with recommended scalable areas) and savings proposals from commands prior to 7P Assessment agreed for inclusion in the next stage of the budget setting process. | Extraordinary SCCB in the morning of 11th or could go with 7th or 8th Oct
S9 | Savings | Corporate Finance Non Pay & Capital Star Chamber: 2 of 3. | Corporate Finance | BPs and MA s | 2021-09-10 | 2023-09-15 | Review of current year forecasts to identify potential saving areas (ensuring no overlap with other savings proposals)
S10 | Savings | Strategic Change commence 7 Pillar Assessment | Force Commands | Chief Officers/Anna Hook | 2021-09-10 | 2023-09-13 | Work to commence after ES&GB
S11 | Savings | Corporate Finance Non Pay & Capital Star Chamber: 3 of 3. | Corporate Finance | BPs and MA s | 2021-09-17 | 2023-09-21 | Review of current year forecasts to identify potential saving areas (ensuring no overlap with other savings proposals)
S12 | Savings | Complete papers for Extraordinary Budget Setting SCCB (Inc. 7 Pillar Assessment) | Strategic Change / Corporate Finance | Debbie Martin / Anna Hook |  | 2023-10-05 | 7 Pillar Assessment completed and returned to Corporate Finance for submission to Extraordinary Budget Setting SCCB
S13 | Savings | SCCB (Extraordiary Budget Setting) | Strategic Change / Corporate Finance | Debbie Martin / Anna Hook |  | Thur-12-Oct | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment.
From this point follow 'Strategic' timetable

## Capital Timetable
Capital - Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Last Yr's Meeting Date | Date | Comments
C1 | Capital | Engagement with Budget Holders commences to discuss existing and new Stage B Capital Investment bids | Corporate Accounting | Arfanara Naidu | 2021-06-28 | 2023-06-26 | Early engagement with Budget Holders to discuss their capital needs.
C2 | Capital | Distribute Template to capture Stage B capital bids for new capital investment | Corporate Accounting | Arfanara Naidu | 2021-07-23 | 2023-06-26 | The template will be the new business case template. This will be distributed earlier if available.
C3 | Capital | Estates Change Board | Corporate Finance | Force Commands | 2021-10-05 | 2023-08-21 | Estates capital bids or significant increases to existing bids (more than 10% or £50k change)
C4 | Capital | DTOB | Corporate Finance | Force Commands |  | 2023-09-05 | Approval of IT Capital Bids or significant increases to existing bids to progress to SCCB
C5 | Capital | Deadline for updates to exisiting Stage B bids and new Stage B bids to be submitted to Corporate Accounting. (Other) | Force Commands |  |  | 2023-09-01 | Deadline is for 'other' Capital bids. Estates and IT will have other internal governance boards to accommodate which will require earlier deadlines if finance QA required beforehand
Capital - Timetable Cont.
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Last Yr's Meeting Date | Date of Meeting | Comments
C6 | Capital | Send reviewed new capital bids to Strategic Change for 7 Pillar Assessment | Corporate Accounting | Arfanara Naidu | 2021-09-06 | 2023-09-11
C7 | Capital | 7 Pillar Assessment of new Capital Bids | Strategic Change | Strategic Change | 2021-09-27 | 2023-10-06 | Assessment completed and returned to Corporate Finance for submission to extraordinary SCCB
C8 | Capital | SCCB (Extraordinary Budget Setting) | Strategic Change / Corporate Finance | Debbie Martin / Anna Hook |  | Thur-12-Oct | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment.
From this point follow 'Strategic' timetable

## Pay - Timetable
Pay Budget Setting - Timetable
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Last Yr's Meeting Date | Date | Comments
P1 | Pay | Officer, Staff & PCSO establishment extracted from HR system for pay budget setting (version 1) – as at 1st September 2023. | Business Partnering and Management Accounting | Head of Business Partnering and Management Accounting | 2021-09-01 | 2023-09-01 |  | Corporate A/c Requested from HR. Corporate Accountant put into the pay budget model. RJ Team split up by commands (Dawn) and diseminate to BP team
P2 | Pay | Issue establishment version 1 to HR Advisors and Heads of Department / Commands. | Business Partnering and Management Accounting | Head of Business Partnering and Management Accounting | 2021-09-08 | 2023-09-07 |  | wording of email agree with Richard/ Matt, Mas to make sure that any actions returned to HR are followed through.
P3 | Pay | Establishment version 1 returned by HR Advisors and Heads of Departments / Commands to CFO | Force | HR Advisors/Heads of Depts | 2021-09-17 | 2023-09-21
P4 | Pay | Deadline for COG approved establishment changes to be sent to Organisational Management team to be included in pay budget setting. Any COG approvals after this date will require budget setting process approval | Business Partnering and Management Accounting | Head of Business Partnering and Management Accounting | 2021-10-08 | 2023-10-06 |  | this is the last HR tracker.
P5 | Pay | CFO review of draft provisional pay budget setting information (1 of 2) | Financial Strategy | Head of Financial Strategy | 2021-10-05 | 2023-10-10
P6 | Pay | CFO review of draft provisional pay budget setting information (2 of 2) | Financial Strategy | Head of Financial Strategy | 2020-10-23 | 2023-10-20
P7 | Pay | Provisional Pay Budgets sent to CFO. | Financial Strategy | Head of Financial Strategy | 2020-10-30 | 2023-10-27
From this point follow 'Strategic' timetable

## Strategic Timetable
Strategic - Timetable
Budget Version
Ref | Category of Activity | Activity Description | Responsible Team | Activity Owner | Date | 1. June Strategic Board | 2. Sept Strategic Board | 3. COG Workshop 1 | 4. Dec Strategic Board | 5. Post HO Funding Announcement | 6. Police, Fire, Crime Panel | Comments
ST1 | Strategic | March Strategic Board - Paper Deadline | Corporate Finance | Debbie Martin | 2023-02-20 | [6 empty] | Send MTFS (Q4 based on Month 10) to PFCC for Strategic Board
ST2 | Strategic | Strategic Board - March | Corporate Finance | Debbie Martin | 2023-03-01 | [6 empty] | 2024/25 Draft Budget Setting Timetable and MTFS (Q4 based on Month 10) presented to Strategic Board
ST3 | Strategic | Meeting with PFCC S151 Officer re MTFS Q1 | Corporate Finance | Debbie Martin | 2023-05-15 | [6 empty] | Meeting to discuss MTFS ahead of COG report being finalised
ST4 | Strategic | Initial Budget Setting Paper submitted to Police, Fire and Crime Panel | PFCC | Janet Perry | 2023-05-31 | [6 empty] | Budget Setting Paper captures future budget setting activity / process / timetable
ST5 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2023-06-07 | [6 empty] | Paper deadline for MTFS (Q1 based on month 1) report to COG
ST6 | Strategic | June Strategic Board - Paper Deadline | Corporate Finance | Debbie Martin | 0 | [6 empty] | Send MTFS (Q1 based on Month 1) to PFCC for Strategic Board (Draft as ahead of COG)
ST7 | Strategic | COG - MTFS Update | Corporate Finance | Debbie Martin | 2023-06-14 | [6 empty] | MTFS (Q1 based on Month 1) presented to COG.
ST8 | Strategic | Police, Fire & Crime Panel Meeting | PFCC | PFCC | 2023-06-15 | [6 empty] | Presentation of Budget Setting Paper describing activities and process/timetable for budget setting
ST9 | Strategic | Strategic Board - June | Corporate Finance | Debbie Martin | 2023-06-22 | [6 empty] | Review of MTFS (Q1) presented to Strategic Board (based on report presented to COG on 14th June). Draft paper to be circulated to PFCC Office 13th June.
ST10 | Strategic | Timetable distributed to Budget Holders | Corporate Finance | Annette Chan | 2023-06-23 | [6 empty] | Budget Setting Timetable distributed to Budget Holders
ST11 | Strategic | Extraordinary SCCB | Force Commands/ Strategic Change | Chief Officers / Anna Hook | 2023-08-31 | [6 empty] | Extraordinary SCCB meeting to consider progress on savings proposals
ST12 | Strategic | Police, Fire & Crime Panel Meeting paper Info to the PFCC | Corporate Finance | Debbie Martin | 2023-09-04 | [6 empty] | Format to be agreed. Will form basis of papers going to Police, Fire & Crime Panel 28th September
ST13 | Strategic | Meeting with PFCC S151 Officer re MTFS Q2 | Corporate Finance | Debbie Martin / Janet Perry | 2023-09-08 | [6 empty] | Meeting to discuss MTFS going to Sept Strategic Board ahead of COG report being finalised
ST14 | Strategic | Efficiency Savings and Growth Board | Strategic Change | Anna Hook | 2023-09-12 | [6 empty] | Overall Consolidated Growth Programme (with recommended scalable areas) and savings proposals from commands prior to 7P Assessment agreed for inclusion in the next stage of the budget setting process.
ST15 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2023-09-13 | [6 empty] | Paper deadline for MTFS (Q2 based on month 5) report to COG on 21st Sept
ST16 | Strategic | Police, Fire & Crime Panel Meeting paper deadline | PFCC | Janet Perry | 2023-09-13 | [6 empty] | Papers will be based on June Strategic Board position
ST17 | Strategic | September Strategic Board - Paper Deadline | Corporate Finance | Debbie Martin | 0 | [6 empty] | Send Draft MTFS paper (Q2 based on Month 5) to PFCC for Strategic Board. An Updated paper may be required following consideration by COG on 21st September
ST18 | Strategic | COG - MTFS, Investment and Savings Update | Corporate Finance | Debbie Martin | 2023-09-20 | [6 empty] | Update of MTFS (Q2 based on Month 5) presented to COG with highlevel view of Investment and Savings. Would include latest position submitted for Efficiency, Savings and Growth Board on 12th September.
ST19 | Strategic | PFCC Engagement - Meeting (Sept) | Corporate Finance | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2023-09-25 | [6 empty] | MTFS latest position. Discussions will be based on Sept 23 Strategic Board Paper submission
ST20 | Strategic | Strategic Board - Sept | Corporate Finance | Debbie Martin | 2023-09-26 | [6 empty] | Review of MTFS (Q2) presented to Strategic Board (based on report presented to COG on 20th Sept).
ST21 | Strategic | Police Fire & Crime Panel | PFCCs Office | PFCCs Office | 2023-09-28 | [6 empty] | Based on June Strategic Board position.
ST22 | Strategic | Provision of Papers to PFCC Office for the PF&CP Budget Working Group (1) | Corporate Finance | Debbie Martin | 2023-10-02 | [6 empty] | Format to be agreed. Will form basis of papers going to Budget Working Group (1) on 10th Oct
ST23 | Strategic | Provision of Papers to panel working group (1) | PFCCs Office | Janet Perry | 2023-10-06 | [6 empty] | Papers based on Sept Strategic Board. Format of papers to be determined.
ST24 | Strategic | Police Fire & Crime Panel Budget Setting Working Group (1) | PFCCs Office | PFCCs Office | 2023-10-10 | [6 empty] | PFCC Engagement with the Police, Fire and Crime Panel, Budget Setting Working Group.
ST25 | Strategic | SCCB (Extraordinary Budget Setting Meeting) | Force Commands/Strategic Change | Chief Officers / Anna Hook | Thur-12-Oct | [6 empty] | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment.
ST26 | Strategic | Draft Budget (Exc Pay) sent to CFO | Corporate Finance | Annette Chan | 2023-10-13 | [6 empty] | First draft of budget model consolidating current growth and savings (excluding pay budgets) provided to CFO
ST27 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2023-10-13 | [6 empty] | Paper deadline for COG Budget Workshop 1 or 2. (Revenue + Capital Bids, savings and MTFS - Excludes Pay)
ST28 | Strategic | Meeting with PFCC S151 Officer for PFCC Engagement Meeting | Corporate Finance | Debbie Martin / Janet Perry | 2023-10-16 | [6 empty] | Meeting with PFCC S151 Officer for PFCC November Budget Workshop (Excluding Pay)
ST29 | Strategic | COG - Budget Workshop 1 (exc. Pay) | Corporate Finance | Debbie Martin / Annette Chan | 2023-10-18 | [6 empty] | COG Budget Workshop (1 of 2) – review of provisional Capital & Revenue investment, savings and MTFS. Pay budgets not included.
ST30 | Strategic | PFCC Engagement - send papers | Corporate Finance | Debbie Martin / Annette Chan | 2023-10-19 | [6 empty] | Send update of Capital & Revenue Budget investment, MTFS and savings report to PFCCs Office for Engagement Meeting (Post COG Workshop)
ST31 | Strategic | Provision of Papers to PFCC Office for the PF&CP Budget Working Group (2) | Corporate Finance | Debbie Martin | 2023-10-19 | [6 empty] | Format to be agreed. Will form basis of papers going to Budget Working Group (2) on 2nd Nov
ST32 | Strategic | PFCC Engagement - Meeting (Oct) | Corporate Finance | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2023-10-26 | [6 empty] | Meeting with PFCCs Office to review a précis of Capital & Revenue investment, savings and MTFS. Attended by DCC & CC. - Post COG Workshop
ST33 | Strategic | Chancellors Autumn Budget Statement | N/A | N/A | W/C 23rd Oct (estimated) | [6 empty] | Last Year's Autumn Statement was 27th October
ST34 | Strategic | Provision of Papers to panel working group (2) | PFCCs Office | Janet Perry | 2023-10-30 | [6 empty] | Papers based on Sept Strategic Board. Format of papers to be determined.
ST35 | Strategic | Meeting with PFCC S151 Officer for PFCC November Workshop | Corporate Finance | Debbie Martin / Janet Perry | 2023-11-01 | [6 empty] | Meeting with PFCC S151 Officer for PFCC November Workshop (Excluding Pay)
ST36 | Strategic | Draft Budget (inc Pay) sent to CFO | Corporate Finance | Annette Chan | 2023-11-02 | [6 empty] | Second draft of budget (incorporating pay budgets) provided to CFO
ST37 | Strategic | Police Fire & Crime Panel Budget Setting Working Group (2) | PFCCs Office | PFCCs Office | 2023-11-02
ST38 | Strategic | Efficiency, Savings and Growth Board | Corporate Finance | CFO/Chief Accountant | 2023-11-07 | [6 empty] | Verbal budget update to Efficiency, Savings and Growth Board
ST39 | Strategic | COG - Paper Deadline | Corporate Finance | Debbie Martin | 2023-11-08 | [6 empty] | Paper deadline for COG Budget Workshop 2 or 2. (Consolidated budget proposals with Pay)
ST40 | Strategic | Review of PFCC Budgets (including Pay) | Corporate Finance / PFCC Office | Annette Chan | 2023-11-14 | [6 empty] | Opportunity for PFCC office to review the detailed make-up of calculated 24/25 budget requirement including pay budget setting.
ST41 | Strategic | COG - Budget Workshop 2 (inc Pay) | Corporate Finance | Debbie Martin/Annette Chan | 2023-11-15 | [6 empty] | COG Budget Workshop (2 of 2 inc. pay) – review of provisional Capital & Revenue investement, savings and MTFS. Includes pay and allocation of officer overtime budgets
ST42 | Strategic | Business Community Consultation | PFCC | Darren Horsman | Nov (closing in December) | [6 empty] | PFCC has a duty to consult on the precept. Date not set but held as a place holder
ST43 | Strategic | Meeting with PFCC S151 Officer for PFCC Engagement Meeting | Corporate Finance | Debbie Martin / Janet Perry | 2023-11-21 | [6 empty] | Meeting ahead of engagement meeting with PFCC on 29th November. (Including Pay)
ST44 | Strategic | PFCC Engagement - send papers for Nov meeting | Corporate Finance | Debbie Martin / Annette Chan | 2023-11-23 | [6 empty] | Papers based on latest position (including pay)
ST45 | Strategic | Police Fire and Crime Panel Meeting - Paper Deadline | PFCCs Office | PFCCs Office | 2023-11-23
ST46 | Strategic | PFCC Engagement - Meeting (Nov) | Force | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2023-12-05 | [6 empty] | PFCC & Chief Constable meeting to discuss latest budget setting position.
ST47 | Strategic | Strategic Board - Send Chief Constable Budget Proposal | Corprate Finance | Debbie Martin | 0 | [6 empty] | Draft Budget Proposal sent to PFCC Office (PM)
ST48 | Strategic | Police Fire and Crime Panel Meeting | PFCCs Office | PFCCs Office | 2023-12-07
ST49 | Strategic | Circulation of Growth and Investment Bids included in the Draft Budget to Budget Holders | Corporate Finance | Annette Chan | 2023-12-08 | [6 empty] | Circulated for information and with clear communication that the budget is still subject to PFCC engagement and approval at the Feb Police, Fire & Crime Panel
ST49 | Strategic | COG - Review of Budget Letter | Corporate Finance / Strategic Change | Debbie Martin / Anna Hook | 2023-12-13 | [6 empty] | COG review first draft of budget letter
ST50 | Strategic | Strategic Board (Dec) - Budget Proposals & Officer Investment (Prior to HO Funding Announcement) | Strategic Change | Debbie Martin / Anna Hook | 2023-12-14 | [6 empty] | Strategic Board - Chief Constable presents Budget Proposals including Officer investment (Prior to HO Funding Announcement) | 5
ST51 | Strategic | Home Office Funding Announcement | N/A | N/A | 15/12/2023 - Estimated
ST52 | Strategic | COG Paper Deadline for -Chief Constable's Budget Proposal | Corporate Finance | Debbie Martin | 2023-12-18 | [6 empty] | DM to co-ordinate with input from Strategic Change and Chief Officers. Letter to be finalised for COG virtual review on 19th Dec.
ST53 | Strategic | Update Capital for Stage 2 Approvals at the December Strategic Board (Capital Programme/Rev Cons/Revenue cost of financing) | Corporate Accounting | Matt Tokley | W/C 18-Dec | [6 empty] | Capital position will require updating to feed into budget proposal going to COG Virtual on 19th December
ST54 | Strategic | COG Virtual: Review Chief Constable's Budget Proposal to PFCC (Post HO announcement) | Corporate Finance | Debbie Martin | 2023-12-19 | [6 empty] | Review of Budget post HO Funding Announcement
ST55 | Strategic | PFCC Engagement Meeting - Paper Deadline (Notification of changes following COG Virtual review) | Corporate Finance | Debbie Martin | 2023-12-19 | [6 empty] | Papers for engagement meeting on 20th Dec and Budget Working Group on 4th Jan.
ST56 | Strategic | PFCC Engagement - Meeting (Dec) | Chief Constable | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2023-12-20 | [6 empty] | MTFS/Budget Setting Review post Home Office Funding Announcement (inc adherence to Police, Fire and Crime Plan)
ST57 | Strategic | Provision of Papers to panel working group (3) | PFCCs Office | Janet Perry | 2023-12-29 | [6 empty] | Papers for Budget Working Group on 4th Jan.
ST58 | Strategic | PFCC Engagement - send papers | Corporate Finance | Debbie Martin / Annette Chan | 2024-01-02 | [6 empty] | Send latest budget setting position to PFCCs Office for Engagement Meeting. Include updates from Dec Engagement meeting
ST59 | Strategic | Results from precept survey | PFCCs Office | Darren Horsman | Jan
ST60 | Strategic | Police Fire & Crime Panel Budget Setting Working Group (3) | PFCCs Office | PFCCs Office | 2024-01-04
ST61 | Strategic | PFCC Engagement - Meeting (Jan) | Chief Constable | PFCC/ CC Harrington / DCC Prophet / Debbie Martin/ Janet Perry | 2024-01-05 | [6 empty] | Chief Constable meets with PFCC to discuss Chief Constable's Budget letter
ST62 | Strategic | COG - Final review of Chief Constable's budget proposal letter | COG | COG Members | 2024-01-10 | [6 empty] | COG: Final review of Chief Constable's budget proposal letter post HO funding announcement. (Virtual) - to include Appendicies with subjective summary
ST63 | Strategic | PFCC receives final budget proposal letter | Corporate Finance | Debbie Martin / Annette Chan | 2024-01-12 | [6 empty] | Budget Proposal letter sent to PFCC from Chief Constable (With Supporting Appendicies inc. Subjective Summary)
ST64 | Strategic | Provision of Papers to PFCC Office for the PF&CP Budget Working Group (4) | Corporate Finance | Debbie Martin | 2024-01-12 | [6 empty] | Papers for working group on 18th Jan. Format to be agreed.
ST65 | Strategic | Provision of Panel papers to PFCC | Corporate Finance | Debbie Martin | 2024-01-15 | [6 empty] | Papers due to be submitted by PFCC to ECC on 24th Jan (Budget Letter and supporting appendices)
ST66 | Strategic | Provision of papers to working group (4) | PFCCs Office | Janet Perry | 2024-01-15
ST67 | Strategic | Police Fire & Crime Panel Budget Setting Working Group (4) | PFCCs Office | PFCCs Office | 2024-01-18
ST68 | Strategic | PFC Panel Papers - sent to ECC | PFCCs Office | Janet Perry | 2023-01-18 | [6 empty] | Panel papers including PFCC response to Chief Constable letter sent to ECC for panel.
ST69 | Strategic | Police Fire & Crime Panel | PFCCs Office | PFCC | 2024-02-01 | [6 empty] | PFCC presented budget to panel (2pm)
ST70 | Strategic | PFCC informs Billing Authorities of precept. | PFCCs Office | PFCC S151 Officer | 2024-02-09
ST71 | Strategic | Police Fire & Crime Panel (Reserve Date) | PFCCs Office | PFCC | 2024-02-15
ST72 | Strategic | Internal Budget Book | Corporate Finance | Corporate Accounting | 2023-03-15 | [6 empty] | Circulation of Internal Budget Book to Budget Holders
ST73 | Strategic | Establishment Reports | Corporate Finance | Corporate Accounting | 2023-03-15 | [6 empty] | Establishment Reports circulated to Budget Holders
ST74 | Strategic | External Budget Book | Corporate Finance | Corporate Accounting | 2023-03-31 | [6 empty] | Publication of EP External Budget Book on Website

## Meeting Dates
Key Meeting Dates
Efficiency, Savings and Growth Board
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
|  | 2023-03-07 | Share Budget Setting Timetable. | S1
2021-06-07 | Efficiency, Savings & Growth Board | 2023-07-11 | Initial Strategic discussion on priorities for investment from force growth and presentation of savings proposals received from commands (decisions required on which ones to progress) | S4
2021-09-06 | Efficiency, Savings & Growth Board | 2023-09-12 | Overall Consolidated Growth Programme (with recommended scalable areas) and savings proposals from commands prior to 7P Assessment agreed for inclusion in the next stage of the budget setting process. | S8,ST14
2021-11-22 | Efficiency, Savings & Growth Board | 2023-11-07 | Verbal budget update to Efficiency, Savings and Growth Board | ST38
Estates Change Board |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
| Estates Change Board | 2023-08-21 | Estates capital bids or significant increases to existing bids (more than 10% or £50k change) | C3
2021-10-05 | Estates Change Board | 2022-10-24
Key Meeting Dates Cont.
Digital Transformation Oversight Board (DTOB) |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
| DTOB | 2023-09-05 | Approval of IT Capital Bids or significant increases to existing bids to progress to SCCB | C4
Strategic Change & Co-ordination Board |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
2021-10-05 | SCCB | 2022-07-12 | SCCB - to cover business as usual activity
| SCCB | Thur-12-Oct | Extraordinary Budget Setting SCCB - Review of consolidated Investment (Other), organisational change business cases (some may require subsequent COG approval) and Capital Investment. | IO7, S13, C8, ST25
2021-10-08 | SCCB | 2022-10-11 | SCCB - to cover business as usual activity
COG Dates |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
| COG | 2023-06-14 | MTFS (Q1 based on Month 1) presented to COG. | ST7
2021-09-08 | COG | 2023-09-20 | Update of MTFS (Q2 based on Month 5) presented to COG with highlevel view of Investment and Savings. Would include latest position submitted for Efficiency, Savings and Growth Board on 12th September. | ST18
2021-10-20 | COG | 2023-10-18 | COG Budget Workshop (1 of 2) – review of provisional Capital & Revenue investment, savings and MTFS. Pay budgets not included. | ST29
2021-11-17 | COG | 2023-11-15 | COG Budget Workshop (2 of 2 inc. pay) – review of provisional Capital & Revenue investement, savings and MTFS. Includes pay and allocation of officer overtime budgets | ST41
2021-12-07 | COG | 2023-12-13 | COG review first draft of budget letter | ST49
| COG | 2023-12-27 | Review of Budget post HO Funding Announcement | ST54
2022-01-12 | COG | 2024-01-10 | COG: Final review of Chief Constable's budget proposal letter post HO funding announcement. (Virtual) - to include Appendicies with subjective summary | ST62
Strategic Board |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
2021-06-10 |  | 2023-03-01 | 2024/25 Draft Budget Setting Timetable and MTFS (Q4 based on Month 10) presented to Strategic Board | ST2
2021-06-10 |  | 2023-06-22 | Review of MTFS (Q1) presented to Strategic Board (based on report presented to COG on 14th June). Draft paper to be circulated to PFCC Office 13th June. | ST9
2021-09-27 |  | 2023-09-26 | Review of MTFS (Q2) presented to Strategic Board (based on report presented to COG on 20th Sept). | ST20
2021-12-14 |  | 2023-12-14 | Strategic Board - Chief Constable presents Budget Proposals including Officer investment (Prior to HO Funding Announcement) | ST50
Chief Constable / PFCC Liaison Meetings |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
|  | 2023-09-25 | MTFS latest position. Discussions will be based on Sept 23 Strategic Board Paper submission | ST19
2021-11-05 |  | 2023-10-26 | Meeting with PFCCs Office to review a précis of Capital & Revenue investment, savings and MTFS. Attended by DCC & CC. - Post COG Workshop | ST32
2021-11-24 |  | 2023-12-05 | PFCC & Chief Constable meeting to discuss latest budget setting position. | ST46
|  | 2023-12-20 | MTFS/Budget Setting Review post Home Office Funding Announcement (inc adherence to Police, Fire and Crime Plan) | ST56
2022-01-05 |  | 2024-01-05 | Chief Constable meets with PFCC to discuss Chief Constable's Budget letter | ST61
Police Fire & Crime Panel - Budget Working Group |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
|  | 2023-10-10 | Budget Setting Working Group (1) | ST24
|  | 2023-11-02 | Budget Setting Working Group (2) | ST37
|  | 2024-01-04 | Budget Setting Working Group (3) | ST60
|  | 2024-01-18 | Budget Setting Working Group (4) | ST67
Police Fire & Crime Panel |  |  |  | Timetable Ref
Last Yrs Meeting Dates |  | Meeting Dates |  | Timetable Ref
|  | 2023-06-15 | Presentation of Budget Setting Paper describing activities and process/timetable for budget setting | ST8
|  | 2023-09-28 | Police, Fire and Crime Panel | ST21
|  | 2023-12-07 | Police, Fire and Crime Panel | ST48
2022-02-03 |  | 2024-02-01 | PFCC presented budget to panel (2pm) | ST69
|  | 2024-02-15 | PFCC presented budget to panel (reserve date) | ST71
,